# Purpose

This register lists every dependency for the Guyana Development Bank Lending Application build that sits outside the delivery team. The four-week path to production assumes all of them land. Each line needs a named owner and a committed date. Where a date cannot be committed, say so in Notes so the plan can absorb it rather than discover it in week three.

How to use this document:

- Update your own lines in place. Do not delete rows – instead, strike-through and change font color to red like this.

- Status values: Open, In progress, Committed, Closed, At risk.

- Put the date you last touched a line in the Notes column.

- Raise anything that needs discussion against the question numbers in the next section.

# Open questions

These block work now. Answers needed before the register can be dated end to end.

| # | Question |
| --- | --- |
| Q1 | Bank access (D1). Our working assumption is SFTP batch files sent from the GDB disbursement officer to Bank of Guyana, with confirmations returned as a batch file that updates disbursement and repayment records in our systems. Please confirm or correct. |
| Q2 | My Guyana IAM (D3, T4). GDB lives inside My Guyana. We need My Guyana live for IAM before citizens can reach aLOS, and the interface contract frozen: protocol, token format, claims and error semantics, with no manual fallback. |
| Q3 | Network egress (T2). If My Guyana can reach every external endpoint from the hosting environment, GDB is covered on the same path. Please confirm this holds. |
| Q4 | SMS gateway (T5). The My Guyana team is working on this. Custom gateway or ENET SMPP? We need the answer to build against. |
| Q5 | Email domain authentication (T6). Ministry action or ours? |
| Q6 | Electronic signature (T7). Internal dependency with no named owner. Someone needs to take it. |
| Q7 | Penetration testing (T1). BurpSuite versus the Claude API for agentic pen testing. Internal call, to be settled now rather than late. |

# Top external dependencies

Client-side APIs and access. Everything below is upstream of the build and cannot be worked around internally.

| # | Dependency | Owner | Gates | Status | Target date | Notes / last update |
| --- | --- | --- | --- | --- | --- | --- |
| D1 | Bank access for disbursement and repayment recording, Bank of Guyana | GDB Treasury / the three banks | Disbursement and repayment | Open |  | Mechanism unconfirmed. See Q1. |
| D2 | Credit bureau data-sharing agreement and credit score API | EK Digital | Credit assessment | Open |  |  |
| D3 | My Guyana identity management and Government IAM. Covers e-ID, GECOM, passport, civil registration, GRA tax compliance, DCRA business and Collateral Registry, CHPA land and address, NIS social insurance | EK Digital (My Guyana) / Ministry | Identity, business, address and eligibility verification. Every authenticated journey | Open |  | Single upstream source for all citizen and entity verification. See Q2. |
| D4 | Coursera tenant, API access and published curriculum | Ministry / GDB | Training capability | Open |  | Go-live blocker. |

# Program and data dependencies

| # | Dependency | Owner | Gates | Status | Target date | Notes / last update |
| --- | --- | --- | --- | --- | --- | --- |
| D5 | Sanctions, PEP and adverse-media screening service | EK Digital | Compliance screening | Open |  |  |
| D6 | Credit policy sign-off: assessment criteria, term bounds, arrears treatment | GDB Credit / Board | Underwriting configuration | Open |  |  |
| D7 | Training curriculum content | Ministry of Finance / GDB | Training capability | Open |  | Go-live blocker. |
| D8 | Ministry sign-off on the requirements specification | Ministry of Finance | All build activity | Open |  |  |
| D9 | Nominated operating team for post-hypercare operation and knowledge transfer | Ministry / GDB | Knowledge transfer, hypercare exit | Open |  |  |

# Technology dependencies

| # | Dependency | Owner | Gates | Status | Target date | Notes / last update |
| --- | --- | --- | --- | --- | --- | --- |
| T1 | Penetration testing | Provider | Environment build | Open |  | Tool selection pending. See Q7. |
| T2 | Network egress from the hosting environment to every external endpoint | Provider | Every integration | Open |  | See Q3. |
| T3 | Service domain, DNS and TLS certificates | Ministry ICT | Public launch | Open |  | Requires Ministry ICT confirmation. |
| T4 | My Guyana interface contract frozen: protocol, token format, claims, error semantics, no manual fallback | EK Digital (My Guyana) | Sign-in and every authenticated journey | Open |  | See Q2. |
| T5 | SMS gateway with a registered sender identifier | Provider | One-time passcodes and notifications | Open |  | See Q4. |
| T6 | Email domain authentication on the service domain | To be confirmed | Notification deliverability | Open |  | See Q5. |
| T7 | Electronic signature behind the e-ID: signing service, SDK or certificate authority, exposed through My Guyana | Unassigned | Offer execution | Open |  | No named owner. See Q6. |
| T8 | Observability, backup and restore tooling, and the post-go-live operating model | Provider / Ministry | Production readiness | Open |  |  |

# Escalation

Any line still without an owner and a date after the review cut-off is escalated to the weekly Practice review. Product Owner: Bharat Vedula.

Please loop in anyone from EK Digital, the My Guyana engagement, GDB Treasury and Ministry ICT who owns a line so updates land in one place.