## Implementation Acitivities
Task Name | Status | Depedencies | Comment | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30
SOW | InProgress | bar: 2026-09-08
Loan application workflow | InProgress | bar: 2026-09-08
Architecture & solution design | Pending | bar: 2026-09-08
Citizen Onboarding | bar: 2026-09-08
API/integration design | Pending | GRA Contracts | GRA Team has to share the APIs details to Integrate | bar: 2026-09-11
Database & data model | Pending | bar: 2026-09-11
Customer/Applicant Portal | Pending | bar: 2026-09-17
Loan Product Configuration | Pending | bar: 2026-09-17
Field Assessment & Verification | Pending
Underwriting Assessment | Pending
Sector / Business Assessment | Pending
Customer/Applicant Setup | Pending
Repayment & Loan Servicing | Pending
Approval Matrix | Pending
User, Role & Access Management | Pending
Accounting Integration/ERPNext | Pending
Disbursement Process | Pending
Document Management | Pending | bar: 2026-09-15
Reporting | Pending | bar: 2026-09-15
Deployment to Dev, QA | Pending | bar: 2026-09-21
Deployment to UAT | Pending | bar: 2026-09-25
Testing — SIT, integration | Pending | bar: 2026-09-24
Testing — UAT | Pending | bar: 2026-09-29
Deployment & production readiness | Pending | bar: 2026-09-30